## HL View
Component | Description
Streamlit UI | User uploads docs and chats
FastAPI Backend | Handles APIs: upload, query, chat
Document Processing | Extracts text from PDF/Word/Images
Vector DB (ChromaDB) | Stores and retrieves embeddings
Ollama LLM Layer | Runs llama3 and mistral models for answers/summaries

## Local Env Setup
Requirement | Notes
Python 3.10 or higher | Required for backend and RAG
VS Code or IDE of choice | For local development
Git | For version control
Ollama | For local LLM execution
Models: llama3:8b, mistral:7b, phi3:3b | Pulled via Ollama
Tesseract OCR | Needed for image ingestion
Python libraries: fastapi, uvicorn, streamlit, langchain, chromadb, sentence-transformers, pytesseract, pdfplumber, python-docx, Pillow, rank-bm25 | Install via requirements.txt

## Week 1
Task | Owner | Estimated Hours | Dependencies
Install Ollama and pull models (llama3:8b, mistral:7b, phi3:3b) | All | 1 | Ollama installation
Set up Python virtual environment (venv/conda) | Backend | 1 | Python 3.10+ installed
Create GitHub repo for project | Lead | 1 | Git installed
Set up FastAPI backend skeleton | Backend | 1 | Python env ready
Set up Streamlit UI scaffold (upload + chat) | Frontend | 1 | Python env ready, Streamlit installed
Install and configure ChromaDB for local embeddings storage | RAG Specialist | 1 | ChromaDB installed
Plan high-level architecture including tools (Search, Summarizer) and agent layer | Lead | 1 | Team discussion

## Week 2
Task | Owner | Estimated Hours | Dependencies
Implement PDF ingestion (pdfplumber) | RAG Specialist | 1 | pdfplumber installed
Implement Word ingestion (python-docx) | RAG Specialist | 1 | python-docx installed
Implement OCR for Images (pytesseract) | RAG Specialist | 1 | Tesseract OCR installed
Chunk text and generate embeddings (sentence-transformers) | Backend | 1 | sentence-transformers installed
Store embeddings + metadata in ChromaDB | Backend | 1 | ChromaDB running
Develop Search Tool (BM25 keyword lookup) | RAG Specialist | 1 | rank-bm25 installed
Develop Summarizer Tool (mistral:7b) | RAG Specialist | 1 | mistral:7b pulled in Ollama
Integrate LangChain Agents to invoke tools | Backend | 1 | LangChain installed

## Week 3
Task | Owner | Estimated Hours | Dependencies
Implement /chat endpoint with multi-document retrieval | Backend | 1 | ChromaDB + embeddings ready
Enable agent decision-making: retrieve from multiple sources, merge answers | RAG Specialist | 1 | LangChain agent setup
Implement Chain of Thought workflow: Summarize → Extract Entities → Cross-check → Answer | Backend | 1 | Summarizer tool ready
Integrate lightweight Context Memory (last 2-3 turns stored in session) | Backend | 1 | Session handling in FastAPI/Streamlit
Enable Summarization of large docs (executive summaries) | RAG Specialist | 1 | mistral:7b integrated

## Week 4
Task | Owner | Estimated Hours | Dependencies
Implement Workflow Automation (doc parse → summarize → export CSV) | Backend | 1 | Summarizer + parser ready
Enable offline mode (no cloud APIs, confirm air-gapped execution) | Lead | 1 | All features implemented
Add option to export Q&A session as PDF/Word | Frontend | 1 | python-docx + reportlab installed
UI cleanup (Streamlit sidebar for uploaded docs, better layout) | Frontend | 1 | Streamlit installed
Test all tools: Search, Summarizer, Multi-doc Reasoning, Memory | Testing | 1 | All tools implemented
Final QA, README setup guide, demo preparation | All | 1 | Project complete

## Folder Structure
Folder/File | Purpose
project/ | Root folder
│── app/ | Backend folder
│ ├── main.py | FastAPI entrypoint
│ ├── rag_pipeline.py | RAG + tools pipeline
│── ui.py | Streamlit frontend
│── requirements.txt | Python dependencies
│── README.md | Setup guide